## Sheet1
Task | Due | Status | Description
Board Selection | 2019-05-01 | Complete | Evaluate analog boards that are appropriate for use with standard analytical electrodes. (EnviroDIY Mayfly was selected)
MyWatershedTarget Node | 2019-07-01 | Complete | Develop a target node which posts data to ODM2 Data Portal
Mayfly Source Node | 2019-07-01 | Active | Develop an integration node and other components to integrate with and input data from the EnviroDIY Mayfly data logger
Trend Analysis Node | 2019-07-01 | Active | Develop specialized nodes that signal alerting conditions based on deviation from previous metric patterns
Modular VDAB Publisher | 2019-08-01 | Active | Develop a modular publisher library compatible with EnviroDIY modular sensor library.
Wifi Uplink Radio | 2019-07-15 | Open | Develop capabilities to use WiFI as an uplink between the Mayfly and the PI3-VDAB hub
4G Radio Support | 2019-08-01 | Open | Develop support for 4G communications form the PI3 hub or integrated monitoring station.
Mayfly Control Node | 2019-08-15 | Open | Develop a control node for simplifying setup and control of a Mayfly Data Logger
Mayfly VDAB Sketch | 2019-08-15 | Open | Develop a Mayfly sketch optimized to work with the VDAB Control and Source Nodes.