## Sheet1
Task | Status | DueDate | DueAsDate | Estimate | %Complete | Description
Board Selection | Complete | 01-May-19 | 2019-05-01 | 12 | 100% | Evaluate analog boards that are appropriate for use with standard analytical electrodes. (EnviroDIY Mayfly was selected)
MyWatershedTarget Node | Complete | 01-Jul-19 | 2019-07-01 | 12 | 100% | Develop a target node which posts data to the Monitor My Watershed ODM2 Data Portal
Wifi Uplink Radio | Complete | 01-Jul-19 | 2019-07-01 | 20 | 100% | Develop capabilities to use WiFI as an uplink between the Mayfly and the PI3-VDAB hub
Mayfly Source Node | Active | 15-Jul-19 | 2019-07-15 | 20 | 50% | Develop an integration node and other components to integrate with and input data from the EnviroDIY Mayfly data logger
Trend Analysis Node | Active | 15-Aug-19 | 2019-08-15 | 24 | 20% | Develop specialized nodes that signal alerting conditions based on deviation from previous metric patterns
Modular VDAB Publisher | Active | 01-Aug-19 | 2019-08-01 | 12 | 40% | Develop a modular publisher library compatible with EnviroDIY modular sensor library.
Mayfly VDAB Sketch | Active | 15-Aug-19 | 2019-08-15 | 20 | 40% | Develop a Mayfly sketch optimized to work with the VDAB Control and Source Nodes.
Integrate Depth Sensor | Active | 15-Aug-19 | 2019-08-15 | 10 | 10% | Select, integrate and test a Depth Sensor with the standalone Mayfly Data Logger
4G Radio Support | Proposed |  |  |  |  | Develop support for 4G communications form the PI3 hub or integrated monitoring station.
Mayfly Control Node | Proposed |  |  |  |  | Develop a control node for simplifying setup and control of a Mayfly Data Logger